## Sheet1
Risk Register for VIETNAMESE EAZY
Prepared by: | TungDT |  |  | Date: | 2016-06-07
No | Risk | Description | Category | Root Cause | Triggers | Avoidance plan | Contigency plan | Fallback plan | Potential Responses | Risk Owner | Probability | Impact | Status
1 | Lack of team members |  | People | member out team | Dissatisfied with salary or other members | PM need to have a meeting with this member and suggest him still be there. | Have a meeting to resolve conflict problem | Hire other member |  | MinhNN | low | high
2 | Requirement is changed after project is started |  | Process | SRS not good (not realistic, not feasibility, not meet customer needs) | Customer (user) make change request. Or project team cannot develop the system as desciption in SRS. | Requirement should be paid a lot of attention. SRS should be reviewd carefully by PM and the supervisor. | With each requirement changes, the project tema should have a meeting to analysis the change requests and take actions. | Re-estimate and update plan. |  | MinhNN | high | medium
3 | Team member do not meet the deadline |  | Process | Undisciplined and habit of team member, loose management | Have a deadline | Setting rule and minus of do not meet the deadline: lost money and named at meeting minute. | Punish the member do not meet the deadline. Working over time. | Ask for help from out of team, supervisors. |  | MinhNN | medium | medium
4 | Inability to verify/validate products against requirements. |  | Process |  | Inability to verify/validate products against requirements. | Print out the result to check by normal eyes. Debug into code to see how the code is running | Print out the result to check by normal eyes. Debug into code to see how the code is running | Ask for help from supervisors |  | MinhNN | medium | low
5 | Delivery project doesn’t meet requirement |  | Process | Team member do not understand requirement | Can't delivery project | Teamlead have to review sourcecode and follow requirement | Fix in next version | Extend dealine |  | MinhNN | medium | low
6 | Quality of document which is written by Japanese maybe not good |  | People | Team member do not have much experience working with Japanese | when make document in Japanese | Team member improve Japanese | Refer to the Japanese document | Ask for help |  | MinhNN | medium | medium