## Guildline
Q＆A Management Guildline
1. 目的
Q&A管理表は、プロジェクトチームと顧客間でやり取りされたQ&Aを記録し、フォローアップするために使用されるものである。
メールの中で言及された又は会議（テレビ会議、顧客側にいるオンサイトスタッフとの会議）で提出された質問・確認事項は、
この表に全て記録し、トラッキングをしていく。
Q&Aの重複及び不要な明確化の質問を避けるために、プロジェクトは初めからそのプロジェクトのQ＆A管理担当者を
指定しなければならない。通常はそのプロジェクトのPTL/PMがその担当者となる。読む人を混乱させたり、内容のポイントを
逃さないために、１つのQ＆Aには１つの質問のみ記入するのことを推奨する。
ファイルサイズが大きすぎる場合は、複数のファイルに分けてもよい。その場合、連番（01、02等）はファイル名末尾に
追加する。
2. 範囲
FPTソフトウェアの全開発部門・プロジェクトに適用する。
3. 定義と基準
項番：質問の番号である。
ロケーション：その質問が参照するドキュメントのモジュール・セクションID、要求ID又は件名を表す。
質問：質問の内容である。同じ質問に対するフィードバック又はさらなる明確化の確認がある場合、以下の形式で記入すること。[yyyy/MM/dd FPT/顧客名/人の名前 追加] 例： ＸＹＺが分かりません。 [2006/12/19 FPT追加] ご提案に従うと、弊社はまだ。。。。 最新の追加は赤い字で記入し、関係者がすぐに分かるようにする。
回答：質問に対する答えである。さらに議論がある場合は、質問の明確化ルールを使用する。
重要度： 高 - 作業を滞らせる場合。 中 - 2～4日以内に回答が必要である場合。 低 - 小さな質問。
作成日：- 質問が提出された日。FPTソフトウェア側が記入する。
作成者：- 質問を提出した人。
回答者：- 質問に対する回答を担当する人。顧客側が記入する。
回答期限：回答を受け取る希望予定日
回答日：実際に回答を記入した日。顧客側が記入する。
ステータス： オープン： 質問にまだ答えられていない。 確認済： 質問に十分な答えが得られた。 キャンセル： キャンセルされた。 確認中： 質問に回答があるが、十分ではない。
結論：結論を記入する。FPTソフトウェアが理解したこと又は実行することが分かるように詳細かつ明確に記入する。
質問種別：質問の種類 明確化 - FPTソフトウェアが十分に理解していない内容・課題について説明を求める。 確認 - FPTソフトウェアが顧客に提案したソリューションについて顧客の確認を求める。 顧客側不具合 - 質問で述べている問題は顧客の不具合である。
タイトル： 質問の内容を簡潔に記入する。
プロセス：提出された質問が属するプロセス・活動である。プロジェクトのニーズに応じて、プロジェクトごとにカスタマイズできる。通常は以下の通り。
要求： ユーザの要求、機能仕様又はGUIプロトタイプに関する質問。
設計： 設計、システムアーキテクチャ、詳細設計に関する質問。
コーディング： コーディング、 コーディング規約、コーディング手法に関する質問。
展開： 展開、展開環境、インストールなどに関する質問。
テスト： テスト観点、テスト項目、テスト計画、テスト報告、テストデータ等に関する質問。
プロジェクト管理: プロジェクトの範囲、受入基準、スケジュール、工数変更、作業手順等に関する質問。
4. Q&A管理の手順
FPT
Customer
PM
問題を検出する
Q&Aに記入する
・
仕様が明確でない
・
内部で問題が解決でき
ない
内容を確認する
FPTソフトウェア
質問を送付する
フィードバック
を受け取る
を
・
内容を確認する
・
担当者に送る
・
内容を確認する
・
担当者に送る
解決されない時
指摘し再調査を要求する
回答期限が超過
再調査
-
→催促する
・
内容を確認する
・
結論を記入する
・
解決されない時
再調査する
完了
催促メールを
顧客に送付する
顧客
基本的に1日1回

## Q&A Management
Q&A Management Sheet
| Project code： | Veazy
| Q&A Manager： | QuanNH
| Last updated | 2016-05-20
| Open item | 0
| In Progress item | 0
| Closed item | 10
| Canceled item | 0
| Total | 10
No | Location | Question | Answer | Priority | Creation Date | Creator | Answerer | Reply deadline | Reply date | Status | Conclusion | Type | Title | Process | Notes | Reference
1 | SRS | Vietnamese curriculum is divided into how many levels? List levels. |  | High | 2016-05-17 |  | NgaNTT | 2016-05-19 |  | Closed |  | Definition |  | Requirement
2 | SRS | Which method is used to divide each level into the lesson? |  | High | 2016-05-17 |  | NgaNTT | 2016-05-19 |  | Closed |  | Definition |  | Requirement
3 | SRS | Between levels, is there any difference in structure of lesson? |  | High | 2016-05-17 |  | NgaNTT | 2016-05-19 |  | Closed |  | Definition |  | Requirement
4 | SRS | Mentions the difficulty for foreigners in learning Vietnamese. |  | High | 2016-05-17 |  | NgaNTT | 2016-05-19 |  | Closed |  | Definition |  | Requirement
5 | SRS | Vietnamese curriculum in FPT University is divided into how many levels? List levels. |  | High | 2016-05-18 |  | NgaNTT | 2016-05-19 |  | Closed |  | Definition |  | Requirement
6 | SRS | Name the popular books and materials using in Vietnamese studies. | [7 empty] | Closed
7 | SRS | The system full name : Vietnamese Study System for Japanese. Can we use "VEAZY" as project code? |  | High | 2016-05-23 |  | SangNV | 2016-05-27 |  | Closed |  | Validation |  | Requirement
8 | SRS | Does system need to backup data of lesson/question when editing? |  | High | 2016-05-23 |  | SangNV | 2016-05-27 |  | Closed |  | Validation |  | Requirement
9 | SRS | Should Content Managers have add/edit function as Editor? |  | High | 2016-06-08 |  | SangNV | 2016-06-10 |  | Closed |  | Validation |  | Requirement
10 | SRS | What is the mechanism of ban/unban system user function? |  | High | 1900-01-07 |  | SangNV | 2016-06-10 |  | Closed |  | Validation |  | Requirement